## Sheet1
Task | Time(hrs) | Date | Description
setting up the project | 2 |  | set up the git repo, app boilerplate with create react app, set up wasm capabilities, set up service worker and web installation
setting up the web hosting | 3 |  | got domain name, pointed domain name at gh-pages server, set up gh-pages cli deloyment
created audio recorder | 4 |  | created a simple demo that records and downloads audio. Will be an essential feature in our app we will design other components around
meetings | 2 |  | communication with group members over discord
meeting | 1 | 2021-11-02 | Just a quick updated. We have all been working on our pieces individually and are getting close to a point where we can start wroking them together.
housekeeping | 3 | 2021-11-05 | just pulling everybody else's code, making sure everything works, and tidying up
project setup | 2 | 2021-11-15 | set up packages so they can be built as libraries with vite and include typescript declarations
percussion feature | 3 | 2021-11-16 | built the percussion package and imported it into the main app
Meeting | 2 | 2021-11-20 | Trying to get on track for next weeks deadline
Pitch finder | 2 | 2021-11-20 | Refactored the pitch finder package so it could be imported
Figma | 4 | 2021-11-22 | Learning figma and prototyping a UI
Meeting | 0.5 | 2021-11-22 | just getting everyone on the same page
created UI and style | 6 | 11-23 - 11-24 | took the desig I created in figma and wrote scss stylesheets and basic react component structure
create audio inputs | 8 | 11-25 - 11-26 | created the forms at the top of the page for recording and uploading audio files
create audio processing | 8 | 11-27 - 11-28 | pulled in the other libraries built by my other members and added there functionality to the UI
meeting | 0.5 | 2021-11-29 | just a short meeting preping for the demo the next day.
polishing the features | 6 | 2021-11-29 | just making sure the forms and ui work as expected, disabling the right elemets, giving the use error message feedback, and improving the overall UX.