## Sheet1
Task | Time (hrs) | Date | Description
Meeting | 1 | 2021-10-10 | Brainstormed ideas for features and set our first objectives to learn javascript and be able to record a hub
Learn JavaScript | 12+ | Oct 10 - Oct 20 | I learned Javasript but I also learned some HTML and CSS
Meeting | 0.5 | 2021-10-19 | Assigned each person an aspect of the project they would be responsible for
Make Percussion Functionality | 3 | Oct 21 - Oct 22 | Got the basics of a drum machine going using the tone.js API
Make Percussion Functionality | 2 | 2021-10-24 | Continued work on drum machine trying to add simple functionality
Make Percussion Functionality | 4 | 2021-10-25 | Decided to use WebAudio API rather than tone.js. I spent some time learning it and then building a new drum machine
Make Percussion Functionality | 15+ | Oct 26- Oct 30 | Drum machine can load recorded audio, fit it to drum machine, detect tempo, and can be edited. There is an issue with playing tho
Make vite for Percussion and fix bug | 2 | Nov 1 - Nov 2 | Fixed bug. It plays now and can be edit on the fly. Made the vite for it and added it all to the repo
Meeting | 0.5 | 2021-11-02 | Discussed how progress was coming
Improve Percussion and add Functionality | 5 | Nov 7 - Nov 8 | Made some improvement to the code and added the ability more capibilities to manipulate the drum machine. Multiple files can be loaded well now
Improve Percussion and add Functionality | 5 | Nov 13- Nov 14 | Made general improvements to make the perccussion portion more usable. Loaded drum files stretch to fit each other
Export functions and Seperate Dom manipulation | 2 | 2021-11-15 | I exported items needed to operate the drum machine and seperated the functionality from the DOM manipulation. Put export items and helper function in seperate files
Meeting | 2 | 2021-11-20 | Getting ready for the next deadline
Work on rythmic aspect of pitch detection | 6 | Nov 20 - Nov 21 | Using some things similar to percussion I made a couple functions to get the quantization and tempo of a hummed melody
Meeting | 0.5 | 2021-11-22 | Discussed what was need in this last week before the deadline
Make my code easier to integrate | unkown | Nov 21 - Nov 28 | Made changes that Abram suggested to make integration easier and moved more unessesary items into the helper.ts file
Meeting | 1 | 2021-11-28 | Getting all the code put together nicely
Get ready for Demo day | 6 | 2021-11-29 | Fixed bugs, added some functionality, improved the quality of some of the code, made a function to export the drum machine audio as a .wav file
Final touches and report stuff | 3 | 2021-11-30 | Fixed some bugs that I had previously not noticed and worked on getting the report done